## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | Key members may leave the project, impacting progress and team efficiency. | 2 | 3 | 4 | 48 | team leader and all members | 2024-10-08 | Strengthen team bonding and provide incentives to boost team cohesion. | No one dropped the class so far | Close
| add new team members | New members may slow down the project due to a learning curve or lack of familiarity. | 1 | 1 | 1 | 25 | team leader and all members | 2024-09-16 | Provide detailed documentation and necessary training to ensure new members adapt quickly. |  | Close
| Lack of motivation or responsibility | Some team members may not be sufficiently motivated, leading to delays or incomplete tasks. | 3 | 4 | 3 | 18 | team leader and all members | 2024-12-05 | Set clear goals and performance assessments, provide regular feedback. |  | Open
Communication | duplicate work | Two or more team members may unknowingly work on the same task, wasting time and resources. | 3 | 2 | 2 | 24 | team leader and all members | 2024-12-05 | Implement clear communication channels and use project management tools for task assignment. |  | Open
| worked on wrong components | Team members may misunderstand task assignments and work on incorrect components. | 3 | 3 | 4 | 36 | team leader and all members | 2024-12-05 | Clarify roles and responsibilities, use task assignment tools to ensure transparency. |  | Open
| useless work | Tasks completed may not contribute to the project’s core objectives or goals. | 4 | 3 | 3 | 18 | team leader and all members | 2024-12-05 | Regularly review task progress to ensure work aligns with project goals. |  | Open
| inconsistent work | Variations in work quality or style among team members may affect the overall system quality. | 4 | 4 | 4 | 16 | team leader and all members | 2024-12-05 | Establish consistent development standards and perform regular code reviews. |  | Open
Requirements | unclear requirements | The system requirements may not be clearly defined, leading to confusion during development. | 3 | 4 | 4 | 24 | Design and Implementation Leader | 2024-12-05 | Conduct regular meetings with BU students to clarify and ensure well-defined requirements. |  | Open
| scope creep | The project scope may expand beyond initial expectations, leading to delays and additional work. | 4 | 3 | 3 | 18 | Design and Implementation Leader | 2024-12-05 | Define a clear project scope and establish a change management process. |  | Open
| User Verification Risk | The platform’s trust relies on ensuring only BU students can register. If the verification process fails, unauthorized users may access the platform. | 4 | 3 | 3 | 18 | Design and Implementation Leader | 2024-12-05 | Implement strong validation processes, potentially integrating BU's authentication system. Regularly audit user accounts. |  | Open
| constant requirements changes | Frequent changes in requirements can disrupt the development process and delay milestones. | 3 | 4 | 3 | 18 | Design and Implementation Leader | 2024-12-05 | Assess the impact of changes and adjust development priorities accordingly. |  | Open
Management | improper task assignments | Tasks may be assigned without considering team members’ skill levels or availability. | 3 | 4 | 2 | 12 | Team leader and Implementation Leader | 2024-12-05 | Ensure task assignments are aligned with each team member's strengths and expertise. |  | Open
| improper planning | Poor planning may result in mismanagement of resources, causing project delays. | 3 | 3 | 3 | 27 | Team leader and Implementation Leader | 2024-12-05 | Create detailed project plans, monitor progress regularly, and make adjustments as needed. |  | Open
| lack of management skills | Team leaders may lack the necessary skills to effectively manage the project. | 1 | 2 | 3 | 60 | Team leader and Implementation Leader | 2024-12-05 | Provide management training to ensure team leads have the necessary project management skills. |  | Open
Technology competence | Not familiar with Spring Boot or Vue.js | Some members may not have enough experience with key frameworks used in the project. | 4 | 3 | 2 | 12 | Design and Implementation Leader | 2024-11-07 | Provide training and learning resources, organize code reviews and knowledge sharing sessions. |  | Close
| LLM Integration Risk | Integrating LLM technology (e.g., LLaMA) into the platform may present technical challenges, especially in performance and accuracy. | 4 | 3 | 3 | 18 | Design and Implementation Leader | 2024-12-05 | Gradually integrate LLM, starting with small-scale tests. Continuously monitor performance and feedback, iterating as needed. |  | Open
| Not familiar with MySQL | Limited knowledge of the database system could slow down development or lead to inefficiencies. | 3 | 3 | 3 | 27 | Design and Implementation Leader | 2024-11-07 | Provide database management training and best practice sharing sessions. |  | Close
| Not familiar with unit testing | Lack of experience in unit testing could lead to insufficient coverage and untested features. | 2 | 3 | 2 | 24 | Design and Implementation Leader | 2024-11-07 | Establish unit testing standards and provide training for the team. |  | Close
| Not familiar with Git | Inexperience with Git may cause integration issues and inefficient version control management. | 3 | 2 | 2 | 24 | Design and Implementation Leader | 2024-11-07 | Provide Git training and create a usage guide for the team. |  | Close
Design and implementation | Improper system design | System architecture may not meet project requirements or performance goals. | 3 | 3 | 4 | 36 | Design and Implementation Leader | 2024-11-07 | Conduct design reviews to ensure the architecture meets user requirements. |  | Close
| Recommendation Algorithm Risk | Developing the recommendation algorithm based on user data may be more complex and time-consuming than anticipated. | 4 | 4 | 3 | 12 | Design and Implementation Leader | 2024-12-05 | Start with a basic recommendation model based on user behavior, gradually refining it. Regularly review and test its effectiveness. |  | Open
| Incorrect technology stack | Choosing the wrong technology stack can cause inefficiencies or difficulty in future scalability. | 3 | 3 | 3 | 27 | Design and Implementation Leader | 2024-11-07 | Evaluate the chosen technology stack to ensure it fits project needs and scalability. |  | Close
| Messy code | Poor code organization can lead to difficulties in future maintenance and updates. | 4 | 3 | 3 | 18 | Design and Implementation Leader | 2024-12-05 | Implement code standards, and conduct regular code reviews and refactoring sessions. |  | Open
Testing | Insufficient testing | Lack of thorough testing may leave undetected bugs, impacting user experience. | 3 | 2 | 2 | 24 | QA Leader | 2024-12-05 | Create a comprehensive test plan, covering unit tests, integration tests, and user acceptance tests. |  | Open
Integration and deployment | Not enough time for integration and deployment | Tight project timelines may lead to rushed integration or deployment, risking system stability. | 2 | 3 | 2 | 24 | Configuration Management Leader | 2024-12-05 | Plan for integration and deployment early, allocating enough time for testing and adjustments. |  | Open
| Cloud Deployment and Scalability Risk | Cloud deployment using Docker and Kubernetes may encounter complexity, especially when traffic increases and scaling is required. | 3 | 3 | 3 | 27 | Configuration Management Leader | 2024-11-07 | Conduct performance and stress tests during the early stages, use auto-scaling features in Kubernetes, and prepare a contingency plan for performance issues. |  | Close
Security | Payment and Transaction Security Risk | Handling users' payment information and transaction details poses significant security risks, such as data breaches or financial losses. | 4 | 4 | 4 | 16 | Security Leader and Implementation Leader | 2024-12-05 | Use industry-standard encryption protocols (e.g., SSL/TLS), secure payment gateways, and regularly conduct security tests to identify and fix vulnerabilities. |  | Open