## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 1 | 4 | 4 | 40 | team leader and all members | 2024-09-10 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more new team members. | 1 | 2 | 4 | 80 | team leader and all members | 2024-09-10 | The school's course selection period has passed and there will probably be no new members joining.If a new team member joins, assign them to help according to the current progress and their strengths. | No new added the class so far
Communication | duplicate work | Team members work on the same task due to unclear responsibilities | 2 | 5 | 3 | 12 | team leader and all members | 2024-09-10 | Use Jira to assign clear responsibilities to each team member, ensuring that tasks are not duplicated. Conduct regular task reviews in Jira to track each member's progress and verify that no one is working on the same task. Set up weekly check-ins to discuss task status and resolve any potential overlaps. | After two meetings, the project theme was finalized, and we agreed to use Jira for task management and progress tracking. Everything is progressing smoothly so far, with no issues reported
| worked on wrong components | Project requirements are not clearly defined, leading to confusion | 3 | 4 | 3 | 18 | team leader and all members |  | Create a detailed project requirements document. Review and update with the latest change in each iteration. | Initial project Project Proposal and Planning created.
| useless work | Team members work on tasks that are later deemed unnecessary due to changes in requirements or misunderstanding of the project goals. | 2 | 4 | 3 | 24 | Team Leader |  | Regular review project to ensure all tasks are aligned with project goal before starting new task. Do only task in current sprint board. | Jira project board to ensure tasks are taken only from the sprint backlog.
| inconsistent work | Team members produce work that lacks consistency in terms of quality or style, often due to unclear guidelines or lack of coordination between team members. | 3 | 3 | 2 | 18 | QA Leader |  | Develop a style guide with review and testing before deliverables.
Requirements | unclear requirements | Project requirements are not fully clear, causing delays in progress | 4 | 5 | 4 | 8 | Requirement Leader |  | Create a detailed project requirements document with clear use cases.
| scope creep | The scope of the project expands beyond initial expectations | 3 | 4 | 4 | 24 | Team Leader |  | Regularly review the project scope and set all epics and tasks based on user stories.
| constant requirements changes | Frequent changes to project requirements, causing rework, disruptions, and delays in meeting deadlines. | 3 | 5 | 4 | 12 | Team Leader and Requirement Leader |  | Communicate the cost before doing any change.
Management | improper task assignments | Tasks are assigned without considering team members' strengths or current workload, leading to inefficiencies. | 2 | 3 | 2 | 24 | Team Leader |  | Assign workload by skill capability. Review weekly to increase or decrease estimation.
| improper planning | Poor project planning results in missed deadlines, lack of resources, or unclear objectives. | 2 | 5 | 4 | 16 | Team Leader |  | Develop project plan with milestone. Use Jira to track and update planning if necessary.
| lack of management skills | Project suffers from inefficient leadership, leading to confusion in task delegation and priority setting. | 2 | 4 | 3 | 24 | Team Leader
Technology competence | Not familiar with the framework used | Team members are unfamiliar with the framework, leading to slow development and increased learning time. | 4 | 3 | 3 | 18 | Design and Implementation Leader and who is unfamiliar | 2024-09-18 | Organize an extra meeting to guide unfamiliar members. Add additional time for tasks if necessary.
| Not familiar with the programming language used | Lack of familiarity with the programming language leads to slow progress and frequent errors. | 3 | 4 | 3 | 18 | Design and Implementation Leader and who is unfamiliar |  | Organize an extra meeting to guide unfamiliar members. Provide online learning resources.
| Not familiar with unit testing | Team members lack knowledge of unit testing, causing poor test coverage and increased debugging time. | 4 | 3 | 2 | 12 | QA Leader |  | Conduct testing automation. Implement mandatory code review with test.
| Other technology incompetence | Team members lack the necessary skills or experience with key technologies, slowing down the project. | 3 | 3 | 3 | 27 | Design and Implementation Leader and who is unfamiliar |  | Identify and provide resources to improve skill on the technologies. Assign other tasks without the technology.
| Not familiar with Git | Team members are unfamiliar with Git version control, leading to mistakes in code merging and tracking changes. | 5 | 3 | 3 | 9 | Configuration Leader and who is unfamiliar | 2024-09-10 | Organize an screen share tutorial to guide unfamiliar members. Ask and answer question right away when facing issues. | Team members have known basic operations for using git and github
Design and implementation | Improper design | The design of the project does not meet user requirements, resulting in the need for redesign or refactoring. | 3 | 5 | 4 | 12 | Design and Implementation Leader
| improper technology stack | The chosen technology stack is not well-suited to the project's needs, leading to inefficiencies and technical debt. |  |  |  | 0
| Messy code | Poor coding practices lead to unmaintainable and error-prone code, increasing future development time. |  |  |  | 0
Testing | Not enough testing | Insufficient testing results in undetected bugs and issues, causing problems after deployment. | 3 | 5 | 4 | 12 | QA Leader |  | Develop testing plan before deploy. Set test coverage requirements.
Integration and deployment | Not enough time for integration and deployment | Lack of proper time allocation for integration and deployment, leading to rushed and faulty releases. |  |  |  | 0
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.