## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | Key members may leave the project, impacting progress and team efficiency. | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Strengthen team bonding and provide incentives to boost team cohesion. | No one dropped the class so far | Open
| add new team members | New members may slow down the project due to a learning curve or lack of familiarity. | [6 empty] | Provide detailed documentation and necessary training to ensure new members adapt quickly.
| Lack of motivation or responsibility | Some team members may not be sufficiently motivated, leading to delays or incomplete tasks. | [6 empty] | Set clear goals and performance assessments, provide regular feedback.
Communication | duplicate work | Two or more team members may unknowingly work on the same task, wasting time and resources. | [6 empty] | Implement clear communication channels and use project management tools for task assignment.
| worked on wrong components | Team members may misunderstand task assignments and work on incorrect components. | [6 empty] | Clarify roles and responsibilities, use task assignment tools to ensure transparency.
| useless work | Tasks completed may not contribute to the project’s core objectives or goals. | [6 empty] | Regularly review task progress to ensure work aligns with project goals.
| inconsistent work | Variations in work quality or style among team members may affect the overall system quality. | [6 empty] | Establish consistent development standards and perform regular code reviews.
Requirements | unclear requirements | The system requirements may not be clearly defined, leading to confusion during development. | [6 empty] | Conduct regular meetings with BU students to clarify and ensure well-defined requirements.
| scope creep | The project scope may expand beyond initial expectations, leading to delays and additional work. | [6 empty] | Define a clear project scope and establish a change management process.
| User Verification Risk | The platform’s trust relies on ensuring only BU students can register. If the verification process fails, unauthorized users may access the platform. | [6 empty] | Implement strong validation processes, potentially integrating BU's authentication system. Regularly audit user accounts.
| constant requirements changes | Frequent changes in requirements can disrupt the development process and delay milestones. | [6 empty] | Assess the impact of changes and adjust development priorities accordingly.
Management | improper task assignments | Tasks may be assigned without considering team members’ skill levels or availability. | [6 empty] | Ensure task assignments are aligned with each team member's strengths and expertise.
| improper planning | Poor planning may result in mismanagement of resources, causing project delays. | [6 empty] | Create detailed project plans, monitor progress regularly, and make adjustments as needed.
| lack of management skills | Team leaders may lack the necessary skills to effectively manage the project. | [6 empty] | Provide management training to ensure team leads have the necessary project management skills.
Technology competence | Not familiar with Spring Boot or Vue.js | Some members may not have enough experience with key frameworks used in the project. | [6 empty] | Provide training and learning resources, organize code reviews and knowledge sharing sessions.
| LLM Integration Risk | Integrating LLM technology (e.g., LLaMA) into the platform may present technical challenges, especially in performance and accuracy. | [6 empty] | Gradually integrate LLM, starting with small-scale tests. Continuously monitor performance and feedback, iterating as needed.
| Not familiar with MySQL | Limited knowledge of the database system could slow down development or lead to inefficiencies. | [6 empty] | Provide database management training and best practice sharing sessions.
| Not familiar with unit testing | Lack of experience in unit testing could lead to insufficient coverage and untested features. | [6 empty] | Establish unit testing standards and provide training for the team.
| Not familiar with Git | Inexperience with Git may cause integration issues and inefficient version control management. | [6 empty] | Provide Git training and create a usage guide for the team.
Design and implementation | Improper system design | System architecture may not meet project requirements or performance goals. | [6 empty] | Conduct design reviews to ensure the architecture meets user requirements.
| Recommendation Algorithm Risk | Developing the recommendation algorithm based on user data may be more complex and time-consuming than anticipated. | [6 empty] | Start with a basic recommendation model based on user behavior, gradually refining it. Regularly review and test its effectiveness.
| Incorrect technology stack | Choosing the wrong technology stack can cause inefficiencies or difficulty in future scalability. | [6 empty] | Evaluate the chosen technology stack to ensure it fits project needs and scalability.
| Messy code | Poor code organization can lead to difficulties in future maintenance and updates. | [6 empty] | Implement code standards, and conduct regular code reviews and refactoring sessions.
Testing | Insufficient testing | Lack of thorough testing may leave undetected bugs, impacting user experience. | [6 empty] | Create a comprehensive test plan, covering unit tests, integration tests, and user acceptance tests.
Integration and deployment | Not enough time for integration and deployment | Tight project timelines may lead to rushed integration or deployment, risking system stability. | [6 empty] | Plan for integration and deployment early, allocating enough time for testing and adjustments.
| Cloud Deployment and Scalability Risk | Cloud deployment using Docker and Kubernetes may encounter complexity, especially when traffic increases and scaling is required. | [6 empty] | Conduct performance and stress tests during the early stages, use auto-scaling features in Kubernetes, and prepare a contingency plan for performance issues.
Security | Payment and Transaction Security Risk | Handling users' payment information and transaction details poses significant security risks, such as data breaches or financial losses. | [6 empty] | Use industry-standard encryption protocols (e.g., SSL/TLS), secure payment gateways, and regularly conduct security tests to identify and fix vulnerabilities.
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.