## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | One member has dropped the class | Open
| add new team members | adding new members that dont know what we are working on and arent familiar with the stack we are working with | 3 | 4 | 5 | 30 | Configuration Leader | 2024-10-29 | Coach up new team members to be able to assit the team | no added members yet | Closed
| Lack of motivation or responsibility | Team members are not able to commit to their responsibilities | 3 | 4 | 4 | 24 | Team Leader | 2024-10-29 | Reassess the responsiblities of each member, and change assignments if needed
Communication | duplicate work | Not clear assignment of tasks and multiple people work on the same task | 3 | 4 | 4 | 24 | Team Leader | 2024-10-29 | Detail exactly which task is assigned to which team member |  | Open
| worked on wrong components | Assignment was not detailed enough | 3 | 3 | 4 | 36 | Team/Implementation Leader | 2024-10-29 | Clear up miscommunication on which specific task to work on |  | Open
| useless work | Unecessary code changes not used to complete a goal | 3 | 5 | 2 | 6 | Implementation Leader | 2024-10-29 | Clearly define what needs to be accomplished and how the task can be completed |  | Open
| inconsistent work | Code is inconsisent or has holes in implementation | 3 | 5 | 3 | 9 | QA | 2024-10-29 | Check completed code for completeness and quality |  | Open
Requirements | unclear requirements |  |  |  |  | 0
| scope creep | Clearly defining all of our requirements would reduce scope creep | 2 | 4 | 4 | 32 | Requirements Leader | 2024-10-29 | Use Jira to complete an Epic, Stories, and tasks so that the entire project is clearly defined and all requirements are broken down as much as possible |  | Open
| constant requirements changes | This is innevitable, so we'll need to have frequent standups to discuss road blocks etc... | 5 | 5 | 5 | 5 | Requirements Leader | 2024-10-29 | Have a clear plan with as much detail as possible. This should eliminate some changes. |  | Open
Management | improper task assignments | Assigning tasks to individuals who already have a full load or don't have the experience can extend project timeline | 3 | 3 | 3 | 27 | Team Leader | 2024-10-29 | Make sure we understand each others skill set. Ask each person if they are confortable with each task they have been assigned and if not find someone who is. |  | Open
| improper planning | This is when the team did not think through each phase of the project | 5 | 5 | 5 | 5 | Team Leader | 2024-10-29 | Requirements, Design/Implementation, testing, and promoting need to be defined from the start |  | Open
| lack of management skills | Management not able to lead a team | 3 | 3 | 3 | 27 | Team Leader | 2024-10-29 | Communicate often with each other. Offer feedback to help teammates if they need something. Set clear goals and expectations. |  | Open
Technology competence | Not familiar with the framework used | Most team members are not familiar with MERN | 4 | 5 | 5 | 10 | Configuration Leader | 2024-10-29 | Configuration Leader to assist with providing resrources to complete goals and tasks |  | Open
| Not familiar with the programming language used | Most team members are familiar with JS but havent worked with it much | 4 | 4 | 4 | 16 | Configuration Leader | 2024-10-29 | Configuration Leader to assist with providing resrources to complete goals and tasks |  | Open
| Not familiar with unit testing | No one is familiar with unit testing | 5 | 5 | 5 | 5 | Team | 2024-10-29 | Team to look into the best way to complete this and ask professor |  | Open
| Other technology incompetence | Not familiar with secuirty | 4 | 4 | 4 | 16 | Team | 2024-10-29 | Team to look into the best way to complete this and ask professor |  | Open
| Not familiar with Git | Team not familiar with how to work GIt or Github | 1 | 1 | 3 | 75 | Configuration Leader | 2024-10-29 | Look up resrouces on Github
Design and implementation | Improper design | Design doesn't match what the desired application is meant to accomplish | 2 | 4 | 4 | 32 | Design and Implementation Leader | 2024-10-29 | Make use of resources to reassess the application design and consult with the professor |  | Open
| improper technology stack | Tech stack functionalities are not used correctly | 2 | 4 | 4 | 32 | Design and Implementation Leader | 2024-10-29 | Make use of resources to reassess the application design and consult with the professor |  | Open
| Messy code | Code is not well-documented nor uses best coding practices | 2 | 4 | 4 | 32 | Design and Implementation Leader | 2024-10-29 | Clean up code and review best practices |  | Open
Testing | Not enough testing | Not Familiar with testing | 3 | 3 | 3 | 27 |  |  | Resreach unit testing tools and discuss with Professor |  | Open
Integration and deployment | Not enough time for integration and deployment | Not finishing up the work needed for the iteration | 3 | 3 | 3 | 27 | Team | 2024-10-29 | Meet up and discuss what is needed to complete the work on time |  | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.