## Summary-GroupIterationProgress
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 09/05-09/26 | 1. We agreed on developing a second-hand trading app, and successfully developed the initial prototype of the product, providing a tangible platform to demonstrate key features and workflows. 2. We have finalized the tech stack: vue.js (frontend), Java springboot and MyBatis (backend), MySQL (database), LLaMA (for AI search and recommendation), Docker and kubernetes (DevOps/CI/CD), Jenkins and PTS (QA testing) 3. We have confirmed Alibaba Cloud as the cloud service provider, solidifying our infrastructure decisions. 4. We adopted Jira for task tracking and GitHub for version control and collaboration. | 1. Initial challenges in configuring Alibaba Cloud services to meet specific scalability and security requirements. 2. Compatibility issues between selected tech stack components during early development stages. 3. Synchronization and merge conflicts in GitHub during collaborative development. | 1. Language barrier among team members, solved by proper documents and clearer communication channels. | Improvement: Implement weekly scrum meetings for better task scoping Plan: Schedule more frequent check-ins or mid-sprint syncs, establish clear ownership for tasks | 0 | 10 | 2 | 2 | 0 | 99.5 | 77.5 | 3 | 23.5 | 13.75 | 14.25 | 5.25 | 1 | 26 | 5.75 | 17.5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## AngLi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 6 | 5 | 1 | 1 - Define the project type 2 - Determine the technical choices for the project |  | 2 | 2 |  |  |  | 0.5 |  | 1 - Define the project type 2 - Determine the technical choices for the project |  |  |  | 3
2 | 09/12-09/18 | 4 | 3 | 1 | 1 - do some project research 4 - "Configure the local environment, install a virtual server, set up a database testing environment, and configure the local Git environment." |  | 2 |  |  |  | 4 |  |  | 1 - do some project research 4 - "Configure the local environment, install a virtual server, set up a database testing environment, and configure the local Git environment." |  |  |  | 3
3 | 09/19-09/25 | 6 | 6 | 1 | 2-Design the architecture implementation diagram. Determine the project's technical choices, including server architecture and software functionality. Define the specific functionalities to be implemented, including basic features, desirable features, and optional features. Determine the clear objectives for each specific feature. |  |  | 10 |  |  |  |  | 6 | High availability design for various nodes (such as databases, load balancers) is already detailed in the diagram |  |  |  | 6

## HungHsu C
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 5.5 | 4.5 | 1 | 0 - learn git branching strategies, git commit guideline 1 - set up for the project 5 - communicate with the team and decided positions 6 - set up git | 3 | 0.5 |  |  |  | 0.5 | 0.5 |  | 1. Set up git and pull request rules on default branch 2. Update the SPPP - Configuration management plan |  |  | 1. disscuss with the team to see if anthing else is needed to be set up 2. decide the langugae and IDE | 1
2 | 09/12-09/18 | 2 | 0 | 2 | 5 - discussion on project topic | [5 empty] | 2
3 | 09/19-09/25 | 4.5 | 3.5 | 1 | 0 - Learn about Cloud service, Docker container, and Kubernetes. 5 - Meet with group about details on the project and plans on each iterations. 6 - close up Lab one branch, open the branch for iteration 0. Work on iteration 0 | 2 |  |  |  |  | 1 | 1.5 |  | 1. Update configuration plan on SPPP 2. Manage Git branches, release iteration 0

## Yuanbin M
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/02-09/08 | 3.5 | 2.5 | 1 | 0 - Learn some S.E. concepts from the lectures 1 - Spend some time looking for the project and its requirements 5 - Join the team and get to know other team members, and chosen project roles | 1.5 | 1 |  |  |  |  | 1 |  | 1. Proposed some project ideas 2. Shared software engineering experience to the team | N/A | N/A | 0 - learn to create teamfile on team repo, learn to write SPPP and other documents. 1 - start with SPPP. 5- Help other team members to come up with the project proposal | 6
2 | 09/09-09/15 | 6 | 4.5 | 1.5 | 0 - Learn to use commands such as "git clone/pull/add/commit/ push" and complete Lab1 assignments. 1 - Continue to look for proposals for the project and begin requirements analysis. 5 - Attend weekly team meeting and discuss proposals and overall architecture. | 2 | 2.5 |  |  |  | 1.5 |  |  | 1. Collaborate with configuration leader and team leader to complete the checkout and push of team files and branches. 2. Assist in making team proposals and complete project description in README.md. | 1. Project proposal conflicts with other teams. 2. Requirements analysis can take a lot of time. | 1. Check with the team leader and confirm with the professor where there is a conflict. (Change the suggestion or keep or enhance it). | 0 - learn to design product design and requirement analysis 1 - Complete a beta version of project requirement. 2 - Design all the frontend pages regardding to requirement. 3 - Help to initial code base and set up the developement env. | 8
3 | 09/16-09/22 | 8 | 6 | 2 | 0 - learn to design product design and requirement analysis 1 - Complete a beta version of product prototype. 2 - Design all the frontend pages regardding to requirement. 3 - Help to initial code base and set up the developement env. | 1 | 2 | 1 | 2 |  | 2 |  |  | 1. Complete the requirement part in SPPP. 2. Complete the project design and confirm with the team (including basic functions and advanced functions, i.e. LLM). 3. Inite the codebase and do a dry run on laptop with instruction documentation. | 1. More and more complex functions/features may take more development time. 2. The requirements document cannot be clearly understood by other team members. | 1.Discuss and develop clear plans with other team members. 2. Learn more from the templates and previews team. | 0 - Learn to design backend service development using api design. 1 - Confirm requirement document with team. 2 - Continue to use HCI for frontend design. 3 - Write code for specific services and apis. | 8

## Yueyihan Q
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 4.5 | 3.5 | 1 | 0 - Learn and familiarize with the operations of github and security leader responsibility 5 - Forming teams and getting to know the members of the group 6 - set up Github account and git | 3 |  |  |  |  | 1 | 0.5 |  | 1. Set up git and github 2. Learn what security leaders are responsible for | 1. No past experience with github teamwork, unfamiliar with manipulation 2. Need to learn about security | 1. Already learned how to use github 2. Spent two weeks studying on my own and asking members of the group to learn what a security leader needs to be responsible for and learn. | 0 - Learn and complete risk management documentation 1 - do some project research 7 - Finish lab1 | 5
2 | 09/12-09/18 | 4.5 | 3 | 1.5 | 0 - Learn and complete risk management documentation Learn vue. 1 - do some project research 5 - discussion on project topic and technology stack 7 - Finish lab1 | 2 | 0.5 |  |  |  | 1.5 |  | 0.5 | 1. Initial completion of riskmanagement documentation | 1. The project needs more novel function | 1. Consider add AI assistant | 3 - Work with the team to complete iteration0 tasks and submit | 5
3 | 09/19-09/25 | 6 | 5 | 1 | 5 - Participation in meetings and discussion of the technical and functional realization of the project 7 - Take minutes of meetings Finish management plan of SPPP documentation | [5 empty] | 1 |  | 5 | 1. Finish management plan of SPPP documentation 2. Update MeetingMinutes of Week2 meeting 3. Finish SPPP_RiskManagement Document | 1. Need to learn vue 2. Need to come up with solutions to some of the risks so that the project can be carried out safely |  | 2 - Perform front-end design 3 - Started front-end development of the project | 8

## Srujana N
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 5 | 4 | 1 | 0 - Learned about the course structure for software engineering, including grading criteria, group project expectations, and semester requirements. Understood concepts like Software Engineering > Programming & AGILE. 1 & 5 - In the first week, we were asked to form teams and hold a kickoff meeting before the next class. I joined the group Discord to connect with students interested in working with the same programming language and frameworks as me—Java and Spring Boot. | 3 | 1 | - | - | - | 1 | - | - | I completed the pre-class survey, detailing my software engineering background and preferred programming language and framework. I also brainstormed project ideas, such as creating an OTP generator with authentication and developing a database-driven website to display large volumes of information. | I encountered some initial challenges in finding a team focused on Java and Spring Boot. | To finalise the team and project in the upcoming week | Attend a group meeting to discuss the upcoming deliverables for the team project | 6
2 | 09/12 - 09/18 | 11 | 9 | 2 | 0 - In class, we discussed major software disasters from the past year, like the CrowdStrike incident with Microsoft, and explored modern SE techniques. We also covered SE ethics, software process models, Agile (features and manifesto), Scrum, and XP. 1 - Our team meeting focused on project requirements: we identified the necessary tools and frameworks, planned the project kickoff, updated milestones and SPPP files, and assigned tasks to each member. LAB 1 requirements also discussed. 2 - We had a team meet about project design and architecture 3 - I downloaded essential software such as Git, Java, Maven, and set up the IDE. Completed Lab 1 by updating the team.md file with my introduction and merging the changes from the lab1 branch to the main branch. 4 - Testing was done through verification of changes on github repository. 5 - Our team leader shared essential deliverable documents, along with JIRA and GitHub details via email. We collaborated through Discord and offline meetings at BU campus to update the team.md file and complete Lab 1. 6 - I downloaded essential software such as Git, Java, Maven, and set up the IDE. I configured the repository by cloning it to my local machine using SSH instead of HTTPS. | 3 | 1 | 1 | 3 | 1 | 1 | 1 | - | In-class deliverable - major Software disaster in last year, Modern SE techniques - I wrote on microservices and their advantages LAB 1 on github and markdown file submitted | I encountered an issue when trying to push changes to our GitHub project repository via HTTPS repository cloning, which led to an access denial. To resolve this, I set up both private and public SSH keys on my local machine (inside .ssh folder) and GitHub. Using SSH repository cloning resolved the issue with pushing team.md file changes to the `lab1` branch. | All issues resolved. | Prepare for iteration 0 (be ready with all required deliverables) | 5
3 | 09/19 - 09/25 | 6 | 4 | 2 | 0 - Discussed in-class about Software Industry Objectives, DevOps and DevSecOps 1 - We analysed our source code for the decided project and viewed output to see if we required any additional functionalities. In release branch we must update all documents like progress report, meeting minutes for iteration 0 2 - Frontend design almost finalised, our iterations 0,1,2,3 etc timeline and tools has been finalised 3 - Source code implemenation on local machine completed alone with website UI with working buttons 5 - communication and collaboration through on campus and discord meets Risk management - we document any code bugs/risks Discussed additional features required for our code: Scrolling page, AI chat bot etc. SPPP file needs to contain architecture diagram tools & requirement 6 - Necessary tools set up | 3 | 0.25 | 0.25 | 0.25 | - | 2 | 0.25 | - | Progress report and SPPP files for release branch finalised. Iteration 0 presentation requiements discussed and PPT kept ready | N/A | Meet with team to discuss next week's plan for Lab 2 | Prepare for iteration 0 presentation on 26th September(be ready with all required deliverables) | 9
4 | 09/26 - 10/03 |  |  |  | 0 - I learnt about other projects, ideas & tools via team presentations for iteration 0 [ex: Sentinment Analysis in Move Rating app.] Our team could benefit from adopting automated unit testing (Jest, JMeter) and pair programming. 1 - Upcoming lab 2, quiz 1 and iteration 1 requirements discussion

## Yingtong Z
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 6 | 5 | 1 | 1 - define high level requirements 5 - make project plan about milestone, send reminders to team members 6 - set up Google Drive |  | 0.5 |  |  |  | 4 | 0.5 |  | 1. Make Milestone project plan 2. Set up Google Drive, Jira, and assign project files to each team member 3. Host kickoff meeting | 1. Too many files to maintain, need to read them through and help team members understand 2. Being too optimistic and urgent about timeline | 1. Make sure I'm familiar with the files. 2. Use Jira to notify team members. | 1 - do some project research 5 - update project plan, send reminders to team members | 3
2 | 09/12-09/18 | 4 | 3 | 1 | 1 - do some project research 5 - update project plan, send reminders to team members |  | 0.5 |  |  |  | 2.5 |  |  | Write MeetingMinutes Week1 - Meeting 2 | 1. New team member comes in, language barrier during meeting 2. New members want to join in, but current team load is full | 1. Find translation tools for online meeting; push team members to speak English during meetings 2. Learn how to say No for the benefit of the team | 1 - lead the team to discuss requirements 5 - colaborate with design leader to breakdown tasks and assign them to the team | 3
3 | 09/19-09/25 | 7 | 6 | 1 | 5 - host weekly meeting, send reminders to team members through Jira 7 - prepare presentation PPT | [5 empty] | 1 |  | 6 | Iteration 0 presenation |  |  | 3 - Start UI/UX design for mobile app | 6