## Summary-GroupIterationProgress
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9-3-24 to 9-12-24 |  | Lost a member, gained a member
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Jake Kelly
Meng Zhou
Raymond Chen
Vishal
Wenli Gai

## Jake Kelly
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/2-9/12 | 8 | 6 | 2 | 5 - preparing for project (PP, Excels, Docs, etc.) | [5 empty] | 8 |  |  | 1. Preparing presentation PP, SPPP, risk management doc, progress report doc, presentation video, and writing Meeting Minutes | 1. Lost one member and gained one member. Not huge issue | 1. Have new member ready for roll | Help set up development plan and continue to update necessary documents | 10

## Meng Zhou
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/2-9/12 | 7 | 6 | 2 | 0 - Learned how to install and use GitHub Desktop for version control. 1 - Participated in discussions to clarify and define project requirements . 5 - Held meetings with teammates to discuss and confirm the project scope and design. Managed communication for task coordination. 7 - Completed the report tasks assigned to me as part of the project deliverables. | 3 | 1 |  |  |  | 1 |  | 2 | 1.Participated in team meetings to discuss project direction and task assignments. 2.Contributed to the overall project design discussions and decisions. 3.Write key sections of SPPP (Software Project Planning and Proposal) 4.Set up Git repository and commit initial test message 5. Participate in initial project iteration presentation (Iteration 0). | 1、GitHub setup encountered some technical difficulties, which were resolved after troubleshooting. 2、During meetings, there were sound issues with equipment, leading to a reliance on text-based communication. | 1.Continue learning Git usage to further enhance version control management. 2.Change equipment and actively participate in subsequent meetings, and strengthen communication on a daily basis. 3.Plan to actively participate in the backend code design and implementation in the upcoming weeks. | 0 - Learning: Continue learning Git usage and Spring Boot framework to improve version control and backend development 1 - Requirement Analysis: Further define and refine project requirements, especially focusing on backend functionality 2 - Design: Participate in the design of backend architecture, specifically around API endpoints and database structure 3 - Implementation: Begin initial coding for backend components, focusing on setting up basic APIs and integrating with the database 5 - Communication/Management: Coordinate with team members to ensure alignment on task distribution and progress, addressing any communication issues that arise | 10

## Raymond Chen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/12 | 7 | 6 | 2 | 0 - Research database options 5 - Come up with ideas, settle project documents and prosentation. 6 - Setup Jira board, Github branch protection | 1 |  |  |  |  | 5 | 1 |  | 5. Write Configuration Management Plan sections of SPPP 5. Contribute in presentation document 5. Participate in presentation video | 5. Stuggle to settle a project idea | 5. Finalized the idea on 2nd meeting and did planning based on the idea. | 0. Learn how h2 database work 2. Create Design document 3. Set up spring boot and database 6. Add user stories in jira | 15

## Vishal
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader, Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/2-9/12 | 7 | 6 | 2 | 0 - research on testing strategy, bug management 4 - define test strategy, code review process, define coding standard 6 - set up git, IDE - IntelliJ, Editor - VSCode 7 - prepare presentation | 3 |  |  |  | 1 |  | 1 | 1 | 1. Write QA section of SPPP 2. Set up git, commit introduction to lab1 branch 3. Participate in Iteration 0 presentation | 1. initial uncertainity in deciding project | 1. decided one of the project ideas given in the Project Description template | 2 - help with design, define entities and attributes 3 - help setup angular 4 - setup e2e, integration testing framework | 10

## Wenli Gai
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/02-09/12 | 7 | 10 | 2 | 0 - learn github desktop, use pull, push and rebase to do tasks in github 6 - set up git 5 - meeting with teammates to clarify roles, settle proposals 7 - research and come up with potiential risk and mitigations, prepare presentation | 3 |  |  |  |  | 1 | 2 | 4 | 1. Write Management part of SPPP 2. set up git, commit introduction 5 - participate in iteration 0 presentation to introduce risk management | 1. not familar with Jira to apply agile to teamwork 2. not familar with github desktop, took some time to set up | watch tutorials about Jira and github/git and ask for help if needed | 0 - continue to learn github desktop 5 - meeting with teammates to make detail back end coding plan 7 - manage the risk may offer during the develop process | 10