## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
Iteration | Date range | Accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | Non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/03 - 09/11 | Decided on our project idea - Health and Wellness Manager Defined tech stack Created project proposal Started on requirements analysis and project plan via Jira board Created figma wireframes | N/A | N/A | N/A | N/A | N/A | 25 | 0 | 25 | 46.5 | 38.5 | 8 | 5 | 10 | 1 | 0 | 0 | 20 | 2.5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Chris
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 + 2 | 09/03–09/12 | 19.5 | 16.5 | 3 | 0 - begin learning REACT, learn to use Jira 1 - define high level requirements 2 - started to draft UML diagram of Workout object 5 - discord, getting REACT tutorial, prepping for meetings, finalizing submission 6 - began investigating heroku and other free hosting services | 4 | 6 | 1 | 0 | 0 | 4 | 1 | 0.5 | 1. Write Proposed High Level Requirements and Management sections of SPPP 2. Organize and take notes during team meetings 3. Record iteration 0 presentation | Some duplicate work My own late submissions cause my classmates to stay up late | Make sure that tasks are clearly divided, make sure to work in communal docs I will need to finalize assignments the day before they are due. | Create UML diagram Update requirements as needed Contribute to database schema (define Workout objects) Test deployment of a simple page Test connection to database Code fitness form and other pages using React | 30

## Abbie
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Eddie
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 9/4-9/11 | 7 | 5 | 2 | 0 - research potential hosts for deployments 1 - define high level requirements, brainstorm ideas 5 - make git configuration plan 6 - set up git branches and protection rules 7 - prepare presentation and SPPP | 2 | 3 |  |  |  | 0.5 | 0.5 | 1 | 1. Write my sections of SPPP 2. Set up git 3. Help prepare presentation | 1. Unsure of what service to host web app with | 1. Research and determine what host to use | 0 - continue to research host candidates 1 - continue to define requirements 5 - set up docker | 6

## Zihao
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader，Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/4-09/11 | 11 | 8 | 3 | 0 - learn git and jira, read video tutorials about React 1 - define security requirements, 5 - make project plan 6 - set up git 7 - research similar products, prepare presentation | 4 | 2 |  |  |  | 1 | 1 |  | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with React, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish React tutorial in 2 weeks, be able to create simple React hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Amanda
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Amanda Yee Your Lead Roles: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06 - 09/11 | 8 | 6 | 2 | 0 - learn git and React, read module notes 1 - help define high level requirements for project 5 - work with team to complete documents required for Iteration 0 6 - set up git 7 - help prepare presentation | 1 | 2 | 0 | 0 | 0 | 4 | 0.5 | 0.5 | 1. Fill out Quality Assurance section of SPPP and contribute to Overview, Related Work and Proposed High Level Requirements sections 2. Set up git, commit paragraph about me to team.md file 3. Add in Testing slide and Figma mockups to Iteration 0 presentation | 1. Limited experience with React framework | 1. Upskill on React via CodeWithMosh tutorial | 0 - continue to learn React 1 - continue to define requirements 3 - start developing 4 - research Jest testing framework | 8